## WBS and Planning
No | Type of task | Description of task | Outputs / Deliverables | Work Package | Responsible person(s) | Deadline (week) | Estimated time | Actual time | Comment
1 | Phase | Analysis
1.1 | Task | Understanding the business |  | 1
1.1.1 | Subtask | Interview | 1.1, 1.2, 2.1 | 1
1.1.1.1 | Subtask | Interview preperation | 1.2 | 1 | Herm | 1 | 3 hours | 2,5 hour
1.1.1.2 | Subtask | Interviews with domain experts (and write up) | 2.1 | 1
1.1.1.2.1 | Subtask | Interview with driver | 2.1 | 1 | Jurian | 1 | 1 hour | 1 hour
1.1.1.2.2 | Subtask | Interview with order & invoices | 2.1 | 1 | Schahab | 1 | 1 hour | 1 hour
1.1.1.2.3 | Subtask | Interview with CEO | 2.1 | 1 | Bas | 1 | 1 hour | 1 hour
1.1.1.2.4 | Subtask | Interview with planning | 2.1 | 1 | Nithi | 2 | 1 hour | 1,5 hour
1.1.1.2.5 | Subtask | Interview with business support | 2.1 | 1 | Herm | 2 | 1 hour | 1 hour
1.1.1.3 | Subtask | Interview documentation | 2.1 | 1 | Chris | 2 | 2 hours
1.1.2 | Subtask | Stakeholder overview | 1.1 | 1 | Schahab | 1 | 45min | 30min
1.2 | Task | Minutes week 1 | 7.2 | 1 | Jurian | 1 | 30min | 30min
1.3 | Task | Work breakdown structure | 2.2 | 1 | Bas, Schahab | 2 | 3 hours | 2 hours
1.4 | Task | Minutes week 2 | 7.2 | 1 | Bas | 2 | 30min | 30min
1.5 | Task | Software requirements specification (SRS) | 3 | 1 |  | 3
1.6 | Task | Minutes week 3 | 7.2 | 1 | Schahab | 3 | 30min
1.7 | Task | Review SRS | 4.1, 7.3 | 1 |  | 4
1.8 | Task | Minutes week 4 | 7.2 | 1 | TBA | 4 | 30min
1.9 | Task | Domain model | 4.2 | 1 |  | 4
2 | Phase | Design
2.1 | Task | GUI design | 5.1, 5.2 | 2 |  | 5
2.2 | Task | Quality and review report | 6 | 2 |  | 6
2.3 | Task | Presentation | 7.1 | 2 |  | 7
2.3.1 | Subtask | Documentation / report | 7.1 | 2 |  | 7
2.3.2 | Subtask | Prepare presentation | 7.1 | 2 |  | 7
2.3.3 | Subtask | Hold presentation | 7.1 | 2 |  | 7
2.4 | Task | Feedback | Unknown | 2 |  | 8
2.5 | Task | Planning | Unknown | 2 |  | 8
2.6 | Task | Design | Unknown | 2 |  | 8
3 | Phase | Implementation
3.1 | Task | Realization | Unknown | 3 |  | 8
3.2 | Task | JavaServer faces & facelets | Unknown | 3 |  | 9
3.3 | Task | Presentation | 14.1, 14.2 | 3 |  | 14
3.3.1 | Subtask | Prepare presentation | 14.1 | 3 |  | 14
3.3.2 | Subtask | Documentation / report | 14.2 | 3 |  | 14
3.3.3 | Subtask | Hold presentation | 14.1 | 3 |  | 14
3.4 | Task | Final software delivery | 14.3 | 3 |  | 14

## Deliverables
No | Deliverable Name | Deliverable description | Work Package | Deadline
1.1 | Stakeholders overview | An overview of all the stakeholders affected by the system | 1 | Week 1
1.2 | Interview questions | A list of all the interview questions along with the intended interviewee | 1 | Week 1
2.1 | Interview results | An written overview of the answers from the interviews
2.2 | Work breakdown structure | A detailed breakdown of all the tasks that need to completed | 1 | Week 2
3 | Initial software requirements specification |  | 1 | Week 3
4.1 | Revised SRS |  | 1 | Week 4
4.2 | Initial domain model |  | 1 | Week 4
5.1 | GUI design document |  | 2 | Week 5
5.2 | GUI prototype |  | 2 | Week 5
6 | Review report |  | 2 | Week 6
7.1 | Presentation | Presentation to present all progress from first quartester | 2 | Week 7
7.2 | Report |  | 2 | Week 7
7.3 | Final SRS |  | 2 | Week 7
7.4 | Final GUI design / prototype |  | 2 | Week 7
8 | Database design |  | 3
9 | Database implementation and tests |  | 3
10 | Software design: class diagram |  | 3
11 | Software design: sequence diagram |  | 3
12 | Implementation business & persistence logic and tests |  | 3
13 | Implementation GUI |  | 3
14.1 | Presentation | Presentation to present end result from project | 3 | Week 14
14.2 | Report | Report containing all important documents from project | 3 | Week 14
14.3 | Final software | The actual software that is created from the project | 3 | Week 14

## Work Packages
No | Work Package description
1 | Analysis
2 | Design
3 | Implementation